| Project Title: | GrowBot |
| --- | --- |

Weekly Status Report

INSTRUCTIONS: Add basic details about your project to quickly align stakeholders.

| 1 | Project Details |  |
| --- | --- | --- |
| Week Ending: |  | Week 3 |
| Project ID: |  | XX-YYYY-01 |
| Project Manager: |  | Krisha Lakhani |
| Project Summary: |  | Automated garden box using live weather data to control temperature, water, and sunlight for optimal plant growth, with smartphone app control. |

INSTRUCTIONS: Document progress toward goals in the form and time and budget.

| 2 | Project Progress |  |
| --- | --- | --- |
| Project Start Date: |  | January 6, 2026 |
| Project End Date: |  | February 9, 2026 |
| % Complete: |  | 60% |
| Overall Budget Spent: |  | 55% spent; 45% remaining |

INSTRUCTIONS: Document the status of each task to understand which tasks are on track for completion and which might need additional attention.

| 3 | Task Status |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Last Week’s Events |  |  |
| Task |  | Status | Completion Progress |  | Notes |
| Requirements & Planning |  | On Track | 100% |  | Finalized all specs |
| Hardware Design |  | On Track | 100% |  | Box design approved |
| Sensor Integration |  | On Track | 100% |  | All sensors working |
| Software Development |  | On Track | 70% |  | Core logic done |
| Weather API Integration |  | On Track | 80% |  | Testing API calls |
| Mobile App Development |  | In Trouble | 40% |  | UI wireframes done |
| Testing & QA |  | On Track | 0% |  | Scheduled for Week 4 |
|  |  | Choose an item. |  |  |  |

| This Week’s Events |  |  |  |
| --- | --- | --- | --- |
| Task | Status | Completion Progress | Notes |
| Software Development | On Track | 85% | Adding automation rules |
| Weather API Integration | On Track | 100% | Complete by end of week |
| Mobile App Development | On Track | 60% | Building core features |
| Hardware Assembly | On Track | 50% | Connecting components |
| Testing & QA | In Trouble | 10% | Initial tests starting |
| Documentation | On Track | 0% | Begins next week |
|  | Choose an item. | xx% |  |
|  | Choose an item. | xx% |  |

INSTRUCTIONS: Identify any issues and risks; then, determine ways to mitigate them to continue moving forward.

| 4 | Key Issues, Risks and Mitigation Plans |  |  |
| --- | --- | --- | --- |
| Project Issue |  | Project Risk | Mitigation Plan |
| Sensor calibration delays |  | Medium | Order backup sensors, extend testing time |
| Weather API rate limits |  | Low | Implement data caching, use backup API |
| App developer availability |  | High | Reassign tasks, consider contractor support |
| Hardware shipping delay |  | Medium | Source from local suppliers if needed |
| Integration bugs |  | Medium | Daily code reviews, automated testing |